## Slide 1
2024
HOWTO Build a Roadmap
2024-01-04

## Slide 2
“Plan the Work”
THEN
“Work the Plan”

## Slide 3
A roadmap is a “best guess” at what you are doing in the future based on what you know today
It is NOT a commitment – but an educated best guess
It is a tool that is used to communicate your work, your teams work, and your need from others in order to make your projects come to life.
It can/should be a reminder of what you need to be paying attention to, working, statusing and closing out.
It will be used by others to see the status of the work in your area, communicate your estimated plan, and how it is tracking
Should be a quick visual to if work is on track and if not – what the plan might look like to get back on track.
What is a Roadmap and Why do we have them

## Slide 4
Create a list of projects (backlog) that you could/should be working on
  For these projects understand what it is, what it is not, who wants it, what benefit it will deliver, and how we will measure success when done (that can all be in your head or written down)
  It would be nice to have some “sizing” estimate also – but not required
Prioritize this list in the order you feel these should be worked
Break down each project into a set of activities that are 1-4 weeks in duration. This will be a list of activities that are bite size chunks that have measurable deliverables in short enough timeframes that we can track it, status us, and determine if we need to replan it
  Requirements, requirements review/approval, design, design review/approval, build (could be a # of different tasks), test, deploy, post deployment support (as typical tasks)
Put this set of task as Gantt bars or milestone triangles onto the form showing the activity, elapsed time, ownership of that task and the status of that activity (in progress, not started, at risk/late, blown, on hold/cancelled) and if required – use lines/arrows to connect things.
Getting Started

## Slide 5
Review your roadmap at least weekly
  Update the time scale in the master slides to show the current time
  Update the status of various tasks to capture current understanding of status of that task
  If there are late/at risk items – use a red arrow to show the current view of the projected completion
    Optionally – in the notes section of the page – write up what caused the delay and how you are recovering.
  Optional set/update the date in the upper right corner to show the last time you looked at and updated that slide.
Replanning
  If a project has gone sideways bad enough that the current timeline is no longer viable, then:
    Duplicate the slide
    Mark “Orig” on the old slide
    Rearrange the new slide to the new plan
  Doing this allows a person to toggle between the old slide and the new slide and visually see the changes
On-Going Maintenance

## Slide 6: Color Code Template – Near Term Work
Last Update: 2024-01-03
Started At Risk Task
Started not completed
2nd shot at task
Completed Early
Completed
Task
Started on track task
Running late with new date
Owner
Hansard
Scott H
Ben L
Arnie
Completed Task
Not Started Task
Praino
Review
Follow on task
Review
Pushed out At RiskTask
Rpt Dev
New complete
date
Not Started
Late Task

## Slide 7: Color Code Template – Longer Term Work
Hypercare
2023-12-17
Incremental Bug Fixes & Enhancements
Stabilize SAP
KT to Existing Staff
SAP Steady State
Knowledge Transfer to New Sierra Support Staff
Staff Requisition Process
PwC transferring Sierra Space
Recruiting
Onboard and Knowledge Transfer of New Support Staff
Sierra Space (Matt H / HR)
Post Go Live Audit
SAP Upgrade to
SAP MSP Plan
CRM Phase 1
BiWeekly Pay
PPM Eval
PPM Phase 1
PPM Project Start
CRM Phase 2
CRM Phase 3
PPM Phase 2
Hyperion – All Capabilites
SNC eCRM #1
SNC eCRM #2
SAP GTS
PPM Phase 3
Not Scheduled
SAP Leasing
New Legal Entity
SAP Accrual Engine
SAP Ariba
COBRA Integration
Vertex – Vendor Recon
Hypercare